## Cutover Plan Stories-Work
Sequence Nbr | Resource Group | Module | Category | Task Name | Predecessors | Name | Production Due Date | Production Status | Notes
1 | MBSE Product Team | MBSE | Setup MBSE Prod | US153808 - Create Category Structure for MBSE-PROD Access Control |  | Silke Mast | 2022-05-16 | Not Started
2 | MBSE Product Team | MBSE | Setup MBSE Prod | US153814 - Remove Internal Users Except Administrator and Guest |  | Bryan Heath | 2022-05-16 | Not Started
3 | MBSE Product Team | MBSE | Setup MBSE Prod | US153815 - Move Projects to Sandbox |  | Silke Mast | 2022-05-16 | Not Started
4 | MBSE Product Team | MBSE | Setup MBSE Prod | US153797 - Verify that no data is locked by users on MBSE-DEV |  | Bryan Heath | 2022-05-16 | In Progress
5 | MBSE Product Team | MBSE | Setup MBSE Prod | US153816 - Setup Collaborator License on MBSE-PROD |  | Bryan Heath | 2022-05-16 | Not Started
6 | MBSE Product Team | MBSE | Setup MBSE Prod | US153820 - Change Collaborator Links on MBSE.deere.com to MBSE-PROD-COLLAB location |  | Silke Mast | 2022-05-16 | In Progress
7 | MBSE Product Team | MBSE | Migrate Users to MBSE-PROD for Initial Release | US153817 - Add Early Adopter Users to new AD Groups |  | Silke Mast | 2022-05-16 | Accepted
8 | MBSE Product Team | MBSE | Migrate Users to MBSE-PROD for Initial Release | US128147 - Implement MBSE-PROD Groups for Access Management |  | Randall Satterthwaite | 2022-05-16 | Not Started
9 | MBSE Product Team | MBSE | Migrate Users to MBSE-PROD for Initial Release | US128146 - Implement MBSE-PROD Roles for Access Management |  | Randall Satterthwaite | 2022-05-16 | Not Started
10 | MBSE Product Team | MBSE | Migrate Users to MBSE-PROD for Initial Release | US153821 - Remove Access to users in early adopters on MBSE-DEV |  | Silke Mast | 2022-05-16 | Not Started

## Cutover Plan Friday May 16 2022
Cutover task | Notes | Optional task | Duration | Date | Time
Check for locked items | Start earlier Friday as preparation |  |  | 2022-05-13 | 7:00AM
Send email | Send email to users to unlock data (need ID and Project as data) |  |  | TBD
Take down Development | take system down |  | 10 minutes | 2022-05-13 | 12:00PM
Remove all internal users | Remove all internal users except for 2 users (Admin & Guest). This task is optional if we run into issue, could move to another down-time if required | X |  | 2022-05-13
Take Full backup | take a full back up of development environment |  | 20 minutes | 2022-05-13 | 12:20PM
Copy DB | copy the DB copy from Dev to Production environment |  | 10 minutes | 2022-05-13 | 12:30PM
Restore/LoadTable | Run the restore process on Production environment |  | 40 minutes | 2022-05-13 | 1:10PM
CAMEO/TWC Security |  |  | 40 minutes | 2022-05-13
Create categories |  |  | 20 minutes | 2022-05-13
Create first level categories in MBSE-Prod | Essentially folder structure |  | 10 minutes | 2022-05-13
Create second level categories for Enterprise Resource Category | Essentially folder structure |  | 10 minutes | 2022-05-13
Add Users and Groups | Add users and groups to Cameo/TWC (Can be completed ahead of cutover) |  | NA | 2022-05-13 | NA
Move MBSE data structure all under sandbox folder | Move folders to Sandbox data structure |  |  | 2022-05-13
Setup Collaborator License | Setup the Collaborator license on Production server |  | 5 minutes | 2022-05-13